## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-10-12 | Yuntian | P3 | resolved | Jiayi | The animated player sprite is not updating consistently and may skip frame while walking. | The sprite should animate consistently in all directions. | The player sprite may stop updating upon change of direction. | Change player direction in the game scene and the bug will appear.
2 | 2024-10-13 | Yuntian | P3 | resolved | Ray | If two of the WASD keys are pressed in the main menu, the player may lose control in the game scene. | The player should move according to the state of the WASD key. | The player keeps moving towards one direction. | Press two of the WASD keys in the main menu. Release one of them to enter the game scene while holding the other one. Release the other one in the game scene. The bug will then appear.
3 | 2024-10-13 | Yuntian | P2 | resolved | Yuntian | The player can squeeze themselves into a specific corner and pass through the wall | The player should be blocked by the wall | The player keeps moving | If the player moves towards the bottom left corner of the map, they will pass through the wall
4 | 2024-11-02 | Yuntian | P2 | resolved | Ray | If the game freezes for long enough, entity may ingore collision and move out of the walls. | All entities' movement should be blocked by the walls | Some entities may pass through walls | Drag the window to freeze the game. If the game freezes for long enough, there is a chance that this issue may arise
5 | 2024-11-02 | Yuntian | P4 | won't fix | Eric | If two hints are attached to the same entity, both of them will be shown when the player approaches | One entity should only display one hint | Two hints may be displayed and overlapped together | No entity in our current release has two hints. Yet it is nice to have a logic to deduplicate the hint texts.
6 | 2024-11-02 | Yuntian | P2 | resolved | Ray | The hand of the player may stick into the gap of the wall tile | The player's movement should be blocked by the walls | The player's hand sometimes can go inbetween the gap between the wall tiles | Face the player to the gaps between the wall tiles and move towards them. There is a chance the hand may go inside of the wall. This is likely due to the sharp shape of the hand and that we optimize the mesh by reduing number of vertices
7 | 2024-11-03 | Jiayi | P2 | won't fix (can't reproduce) | So far didn't know what causes the issue | FPS drops drastically on specific type of machine | A consistant FPS rate regardless of devices | FPS drops from 60 to 20. Low FPS can cause entities pass through wallls | Using my machine: Intel(R) Core(TM) i5-10300H CPU @ 2.50GHz 2.50 GHz; 16.0 GB RAM; 512GB SSD
8 | 2024-11-17 | Yuntian | P2 | won't fix (this is Windows behaviour) | Yuntian | Release WASD key while the game is frozen will cause the player to lose control and move indefinitely in one direciton. | The character should stop moving after the key is released | The chracter moves into one direction indefinitely | Press one of the WASD keys, drag the window to freeze it and then release the kay. After the game restores, the player will move into one direction indefinitely.
9 | 2024-11-17 | Yuntian | P2 | resolved | Yuntian | Enemies will have trouble reaching the player if they are too close to the player in chasing state. | The enemy should try to chase the player and damge the player by overlapping in chasing state | The enemy fails to overlap with the player if gets too close | Move the character around the enemy and there is a chance that you may find an angle such that the enemy thinks that she is overlapped with the player yet due to precise collision, no damage is dealt.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release