## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-10-12 | Yuntian | P2 | open | Jiayi | The animated player sprite is not updating consistently and may skip frame while walking. | The sprite should animate consistently in all directions. | The player sprite may stop updating upon change of direction. | Change player direction in the game scene and the bug will appear.
2 | 2024-10-13 | Yuntian | P2 | open | Ray | If two of the WASD keys are pressed in the main menu, the player may lose control in the game scene. | The player should move according to the state of the WASD key. | The player keeps moving towards one direction. | Press two of the WASD keys in the main menu. Release one of them to enter the game scene while holding the other one. Release the other one in the game scene. The bug will then appear.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release